REVISED PROJECT OUTLINE

Next Steps and Final Report Guidance — Calibrated to AgriCom Expectations

AgriCom / ESMT Berlin   ·   March 2026   ·

# 0.  What This Document Is For

This outline is restructured around AgriCom's stated expectations: credible, logical, empirically grounded results that demonstrate the framework can be tested in practice. This roadmap prioritises analytical honesty and empirical output.

Each section is written with two purposes: as a working instruction for the team (what to do next), and as a guide for the final report (what to include and how to frame it). These are distinguished in the two-column panels throughout this document.

AGRICOM'S STATED EXPECTATION "What matters most to us is seeing credible, logical results that show the proposed approach can be tested in practice." "We are not expecting a large or highly developed model. We are expecting a simple model that is smart, logical, and reflects the market context well." "The strongest final output would combine a clear conceptual framework, a structured testing plan, and initial empirical results that are credible, logical, and grounded in the context."

The implication is direct: stop designing, start running. Even a correlation table and a single regression with honest interpretation is more valuable at this stage than a further elaboration of the model architecture. The architecture work done to date is not wasted — it becomes the conceptual framework section of the final report.

# 1.  Final Report Structure

Before the work plan, it is useful to fix the structure of the final report. Every piece of analytical work in Sections 2–5 maps to a specific section of this report. The report has three parts, each serving a distinct purpose for AgriCom.

| Report section | Purpose | Content source | Status |
| --- | --- | --- | --- |
| Part 1 — Conceptual framework | Show the thinking: why this basket, these segments, these drivers | March 13 update + revised data strategy + hypothesis validation addendum | Complete — needs editing into final report format |
| Part 2 — Testing plan | Show the method: H1–H5 structured and honest about limitations | Hypothesis validation addendum (Addendum B) | Complete — needs condensing to ~2 pages |
| Part 3 — Initial empirical results | Show the evidence: what was actually run and what it found | Sections 2–5 of this outline — to be executed | Not yet started — highest priority |

KEY FRAMING PRINCIPLE FOR THE REPORT The index cannot be fully validated without proprietary demand data, which does not exist. This is not a weakness to hide — it is the honest conclusion of a sound analysis. The report should state clearly that the index is a structured, theoretically motivated proxy for relative demand variation, state what it can and cannot claim, and show that the empirical tests conducted are consistent with the framework's predictions. That combination — transparent limitations plus consistent empirical results — is what AgriCom means by 'credible.'

# 2.  Pricing Data: Contingency Plan

AgriCom has confirmed they can provide weekly Berlin pricing data for all four basket products (organic and conventional). This data has not yet been received. Because it affects the quality of H3 and the price component of the index, the work plan branches depending on whether it arrives before the analytical phase begins.

The contingency is not binary — it is a quality gradient. The framework and hypotheses remain identical in both scenarios. What changes is the precision and credibility of the price-related outputs.

|  | If AgriCom pricing received | If AgriCom pricing not received |
| --- | --- | --- |
| Price variable for index | Weekly ΔP(p,w) from AgriCom data — direct observation | Quarterly ΔP(p,w) from AMI Markt-Bilanz, interpolated to weekly + manual spot checks at 3 stores |
| H3 elasticity test | Genuine own-price elasticity estimation — real coefficient per product with weekly variation | Proxy elasticity only — limited weekly variation, wider confidence intervals, must be labelled as approximate |
| ARIMAX price regressor | Weekly AgriCom price series as exogenous input | Interpolated AMI series — lower frequency, lower confidence in price channel |
| Report framing | Report H3 as an empirical elasticity finding with standard errors | Report H3 as a directional consistency check against literature priors; note data constraint explicitly |
| Manual spot-check protocol | Retain for retail-format comparison only (discounter vs. bio-specialist) | Required as primary price source — 3 stores per week, 4 products, organic + conventional |

RECOMMENDED ACTION Chase the AgriCom pricing data actively before beginning Phase 3 analytical work. Even 8–12 weeks of weekly data is sufficient to run a meaningful H3 regression and populate the price component of the index with real observations. If data is not received by the Phase 3 start gate, proceed with the AMI contingency — do not delay the project.

# 3.  Phase 1 — Data Assembly

| Phase 1 Data Assembly | Weeks 1–2 | IMMEDIATE |
| --- | --- | --- |

All data collection runs in parallel. The output of Phase 1 is a single aligned weekly panel covering January 2021 to present, ready for the exploratory and hypothesis testing work in Phase 2. This is the unglamorous but load-bearing foundation — errors introduced here propagate through every subsequent analysis.

## 3.1  Google Trends panel

| Next step: do this - Export weekly Google Trends data for: bio tomaten berlin, bio gurken berlin, bio paprika berlin, bio salat berlin. Use a single five-term query with bio gemüse berlin as anchor term to preserve cross-product comparability. - Collect January 2021 to present (minimum 260 weeks). Store as tidy CSV: week_start, product, gt_index. - Flag any data gaps — interpolate linearly if ≤2 consecutive missing weeks; exclude longer gaps from regression. - Check for structural anomalies: COVID-period search pattern changes (2021), cost-of-living spike (late 2022). Note these as events to annotate on plots. |  | Final report: include this - Describe the GT panel as the primary demand proxy signal. Show a time-series plot of all four products on the same axis — annotated with key events (heatwaves, Grüne Woche, cost-of-living period). This is the first visual that orients the reader to the data. - Note the known limitation: city-level GT carries higher noise than national data. State that weekly aggregation is the primary mitigation. |
| --- | --- | --- |

## 3.2  Price panel

| If AgriCom pricing received - Merge AgriCom weekly price file (organic + conventional, EUR/kg per product) onto the weekly panel. - Compute ΔP(p,w) = 1 − (P_organic / P_conventional) for each product-week. - Validate: check for implausible values (ΔP < 0 means conventional more expensive than organic — flag these weeks). - Retain AMI quarterly data as a cross-check on the AgriCom series. |  | If AgriCom pricing not received - Obtain AMI Markt-Bilanz Gemüse (3 most recent annual editions). Extract quarterly organic and conventional retail prices for all four products. - Interpolate quarterly to weekly using linear interpolation within each quarter. - Begin manual spot-check protocol: 3 stores per week (1 bio-specialist, 1 full-service, 1 discounter). Record organic + conventional shelf price per kg. - Label all price-derived outputs as 'approximate — based on interpolated AMI data' in report. |
| --- | --- | --- |

## 3.3  External factors

| Next step: do this - Pull Open-Meteo API for Berlin (Tempelhof station): weekly mean temperature (°C), weekly sunshine hours, weekly precipitation. Covering January 2021 to present. - Derive HeatFlag: binary, =1 if weekly mean temperature exceeds 25°C. - Compile public holiday calendar (Destatis) and major Berlin event flags (Grüne Woche, Berlin Marathon, major market events). Binary flag per week. - Pull monthly Berlin Food CPI from Destatis/Eurostat (Code 01). Interpolate to weekly. This is a macroeconomic control only — not a product price proxy. |  | Final report: include this - Include a descriptive table of the external variables: mean, standard deviation, min/max, and number of HeatFlag weeks per year. One paragraph explaining how each variable enters the model. - Do not over-claim weather data: state it is used to test H5 (search-weather correlation) and as a control variable, not as a demand driver in its own right. |
| --- | --- | --- |

## 3.4  Panel alignment

| Next step: do this - Align all series to ISO week identifier (YYYY-Www, Monday–Sunday). Final panel: one row per (week, product) — approximately 1,040 rows. - Completeness audit: flag any variable with >5% missing. Document gaps and treatment (interpolation vs. exclusion). - Produce a single master CSV. Version-control it — any change to the master panel requires re-running all downstream analyses. |  | Final report: include this - Include a one-page data summary table: variables, sources, frequency, coverage period, missing data rate. This directly addresses AgriCom's expectation of a 'structured' and 'practically relevant' approach. |
| --- | --- | --- |

# 4.  Phase 2 — Exploratory Analysis

| Phase 2 Exploratory Analysis | Weeks 2–3 | START EARLY |
| --- | --- | --- |

This is the section that most directly addresses AgriCom's expectation of 'exploratory testing and simple correlations.' It should be completed before hypothesis testing, and several outputs from this phase will appear directly in the final report as standalone findings. The goal is not to test hypotheses — it is to understand the data and build the reader's intuition for the patterns that the hypotheses will then formalise.

## 4.1  Descriptive time-series analysis

| Next step: do this - Plot all four GT series on a single chart, 2021 to present. Add a secondary axis for temperature. Visually identify the summer peaks, the 2022 cost-of-living trough, and any heatwave spikes. - Compute basic descriptive statistics per product: mean GT, standard deviation, coefficient of variation, and peak calendar week (average across years). A high CoV indicates a more seasonally volatile product. - Compute the year-on-year trend in GT for each product: is organic salad search interest growing, flat, or declining over the panel? A simple linear trend line per product answers this. |  | Final report: include this - Include the annotated four-product GT chart as a key figure. This is the most intuitive visual in the report and the one AgriCom will remember. - Include the descriptive statistics table. The peak calendar week column makes the seasonal story concrete: 'cucumber search peaks in week 28 on average; tomato search is more evenly distributed.' - One paragraph on the trend analysis: is the Berlin organic market growing in search terms? This contextualises the basket relevance. |
| --- | --- | --- |

## 4.2  Correlation matrix

| Next step: do this - Compute Pearson correlations between: each product's GT index, weekly mean temperature, sunshine hours, ΔP (price premium), and the Berlin Food CPI. Present as a heatmap or correlation table. - Flag any correlations above 0.6 between predictor variables — these indicate multicollinearity risk that must be acknowledged in the regression stage. - Compute cross-product GT correlations: do the four products move together (suggesting a shared seasonal driver) or independently (suggesting product-specific demand patterns)? Both are informative. |  | Final report: include this - Include the correlation table or heatmap. Even a simple 6×6 table is compelling evidence that the team has understood the data structure before modelling it. - Note any strong predictor correlations explicitly — this is the kind of transparency AgriCom means by 'credible.' Do not hide potential multicollinearity. |
| --- | --- | --- |

## 4.3  Seasonal decomposition

| Next step: do this - Run a simple STL decomposition (statsmodels seasonal_decompose) on each product's GT series. Extract trend, seasonal, and residual components. - Compare the seasonal component across products: which products are most seasonally structured? The ratio of seasonal variance to total variance is a clean one-number summary. - Identify the 'off-season floor': the minimum GT value each product reliably holds across all winters. This is useful for AgriCom as a baseline demand signal. |  | Final report: include this - Include one decomposition plot for the most interesting product (likely cucumbers — expected to show the sharpest seasonal pattern). - Report the seasonal variance ratio for all four products in a simple table. This gives AgriCom a clear ranking of which products are most seasonally predictable. |
| --- | --- | --- |

# 5.  Phase 3 — Hypothesis Testing (H1–H5)

| Phase 3 Hypothesis Testing | Weeks 3–5 | CORE DELIVERABLE |
| --- | --- | --- |

This is the central analytical section and the one that most directly demonstrates the framework is 'analytically sound and practically relevant.' Each hypothesis maps to a specific statistical test. The tests are intentionally simple — correlation, OLS, distributed lag — not because the team lacks capability, but because simple tests with honest interpretation are more credible at this stage than complex models with opaque assumptions.

For each hypothesis, the report should state: the test run, the key result (one number or rank order), and a plain-language interpretation. A verdict of 'partially supported' or 'indeterminate given data constraints' is more credible than forced confirmation.

## H1 — Search-Sales Correlation

What the test is actually testing

Because no sales data exists, H1 cannot test the search-to-purchase link directly. Two proxy sub-tests are used instead. This limitation must be stated in the report — it is not a failure of the methodology, it is an honest characterisation of what public data can support.

| Next step: do this - H1a: Compute the ACF (autocorrelation function) for each product's GT series at the 52-week lag. A significant positive ACF at lag 52 confirms that annual seasonality is a stable, recoverable feature of the search signal — a prerequisite for the signal to be analytically useful. - H1b: Compute Spearman rank correlation of the four products' annual mean GT indices across all five years in the panel. If the rank order (tomatoes > greens > cucumbers > peppers by search volume) is stable (Spearman ρ > 0.80 across years), this supports the hypothesis that search reflects underlying purchasing frequency. - Report both tests. Run in Python: statsmodels acf() for H1a, scipy.stats.spearmanr() for H1b. |  | Final report: include this - Present H1 results with a clear caveat: 'In the absence of sales data, H1 is tested via two proxy sub-tests of search signal stability, not a direct search-to-purchase correlation.' - Show the ACF plot for the product with the clearest seasonal structure (expected: cucumber). One sentence per product on whether annual seasonality is recoverable. - Show the Spearman rank table. If ρ > 0.80, state the rank order is stable. If not, explain which product breaks the pattern and why (e.g. peppers may show more year-to-year volatility). |
| --- | --- | --- |

## H2 — Basket Composite Validity

What the test is actually testing

H2 tests whether the 35/30/20/15 weighting scheme produces a composite index that tracks consumption patterns more faithfully than simpler alternatives. The test is internal to the index — a relative comparison, not an absolute validation.

| Next step: do this - Construct three index variants: (A) proposed 35/30/20/15; (B) equal-weighted 25/25/25/25; (C) tomatoes-only single-product benchmark. - Scale EVS national per-capita consumption volumes to Berlin (pop. 3.7M). Apply organic penetration of 15–20% for fresh vegetables (from BÖLW vegetable sub-category — not the all-food 7% figure). This gives annual synthetic demand benchmarks per product. - Compute mean absolute deviation (MAD) of each index variant from the EVS benchmark across years. H2 is supported if A shows lower MAD than B and C. - Run sensitivity: repeat at α = 0%, +10%, +20% organic penetration. Report all three MAD values — do not report only the scenario most favourable to variant A. |  | Final report: include this - Present the three-variant MAD comparison in a clean table. One paragraph interpreting the result: does the proposed weighting scheme outperform the equal-weight alternative? - State the organic penetration assumption explicitly and show the sensitivity range. This is exactly the kind of transparent assumption-testing AgriCom is asking for. - Frame the conclusion carefully: 'The composite index shows [better/comparable] fit to consumption benchmarks than equal-weighting. This supports the basket construction logic but does not constitute full demand validation.' |
| --- | --- | --- |

## H3 — Price Elasticity Differentiation

What the test is actually testing

H3 tests whether the rank order of own-price elasticity matches the theoretical expectation: bell peppers most elastic, tomatoes and leafy greens least elastic. With AgriCom pricing data, this is a genuine elasticity estimation. Without it, it is a directional consistency check.

| If AgriCom pricing received - Run log-log OLS per product: ln D(p,w) = α + β·ln P(p,w) + γ·PromoFlag + Σδₖ·Qₖ + ε. β is the own-price elasticity. - Report β with 95% confidence intervals for all four products. Test whether the rank order ¦β(pepper)¦ > ¦β(cucumber)¦ > ¦β(tomato)¦ ≈ ¦β(greens)¦ holds. - Compare estimates against published European literature benchmarks (tomato ≈ -0.58 conventional; organic expected larger in absolute value). |  | If AgriCom pricing not received - Run same log-log OLS using interpolated AMI price series. Flag: quarterly interpolation reduces weekly price variation, widening confidence intervals. - Report β estimates as directional only — the rank order test is still valid, but point estimates are less precise. - In report, explicitly label all H3 outputs as 'approximate elasticity estimates subject to price data resolution constraints.' |
| --- | --- | --- |

| Next step: do this - In both cases: check OLS diagnostics — Durbin-Watson for residual autocorrelation, VIF for multicollinearity between price and seasonal dummies. Document and report these. - If Durbin-Watson < 1.5, note that standard errors may be understated and results should be treated as indicative. |  | Final report: include this - Present a four-row elasticity table: product, β coefficient, 95% CI, comparison to literature prior, interpretation. - One key sentence: 'Results are [consistent with / partially consistent with / inconsistent with] the hypothesis that bell peppers exhibit the highest own-price sensitivity in the basket.' - If confidence intervals are wide due to price data constraints, say so explicitly rather than reporting point estimates as if they were precise. |
| --- | --- | --- |

## H4 — Segment Proxy Operationalization

What the test is actually testing

H4 tests whether neighbourhood-level sociodemographic variables predict demand intensity variation across Berlin districts. The test uses district-level GT search demand as the outcome, and income, household composition, age, and organic retail density as predictors. Note the ecological fallacy caveat: this is a spatial pattern test, not a test of individual consumer behaviour.

| Next step: do this - Collect from AfS open data: income per district, single-person household share, population share aged 18–35, migration background share, organic retail density (from OpenStreetMap/Overpass API — bio-specialist and Wochenmarkt count per 10,000 residents). - Construct district-level demand intensity: approximate from GT city-level data using population-weighted shares as a first pass. Note this is an approximation — GT does not provide sub-city disaggregation directly. - Run cross-sectional OLS across all 12 Berlin districts (and Prognoseräume if AfS sub-district data is available): DemandIntensity(d) = α + β₁·Income(d) + β₂·SingleHH(d) + β₃·YoungShare(d) + β₄·MigrationBG(d) + β₅·OrganicDensity(d) + ε. - Run separately for four seasons to produce seasonally-varying spatial demand profiles. Four regressions on 12 districts each — small sample, so interpret directionally. |  | Final report: include this - Present a coefficient table from the H4 regression. Significant positive β₁ (income) supports the Premium Sustainability Buyer segment; significant positive β₂ supports the Convenience-Driven Urban segment; significant positive β₃ supports Modern Plant-Based Urbanites. - Include a Berlin district map showing the predicted demand intensity surface for summer and winter. Even a simple choropleth produced in Python (geopandas) is a compelling visual for AgriCom. - Always include the ecological fallacy caveat: 'These results describe area-level spatial patterns. They do not imply that all residents of high-income districts are premium buyers, or that individual purchasing behaviour can be inferred from district-level data.' |
| --- | --- | --- |

## H5 — Seasonality and Weather Signal

What the test is actually testing

H5 is the most immediately runnable hypothesis and should be completed first. It requires only the GT panel and Open-Meteo data — both fully public and available today. It tests whether temperature and sunshine hours predict search interest, with cucumbers and peppers expected to show stronger weather sensitivity than tomatoes and leafy greens.

| Next step: do this - Run distributed lag OLS per product: GT(p,w) = α + β₀·Temp(w) + β₁·Temp(w-1) + β₂·Temp(w-2) + γ·Sunshine(w) + Σδₖ·Qₖ + ε. - Test cumulative effect β₀+β₁+β₂ for significance using an F-test on the joint restriction. This is the correct test for a distributed lag — not testing each β separately. - Compare cumulative coefficients across products. H5 is supported if cucumber and pepper show significantly larger cumulative temperature effects than tomatoes and leafy greens. - Supplement: identify the five hottest weeks in the panel. Check whether GT indices for cucumber and pepper spike in those weeks relative to the seasonal trend. This is a simple event study that any reader can visually verify. |  | Final report: include this - H5 should appear early in the empirical results section — it is the most visually compelling and most immediately interpretable finding. A scatter plot of weekly temperature vs. cucumber GT index, with a fitted regression line, is intuitive and concrete. - Present the distributed lag coefficient table. Show the cumulative effect and its significance level for each product. - Frame explicitly: 'This result confirms a search-weather relationship for [products]. It supports the inference of a weather-demand relationship, conditional on H1 (search as a demand signal) being validated.' Do not over-claim a direct weather-to-sales link. |
| --- | --- | --- |

# 6.  Phase 4 — Index Construction and Prototype

| Phase 4 Index Construction and Prototype | Weeks 4–6 | INTEGRATES H1–H5 |
| --- | --- | --- |

Phase 4 builds the composite demand index using the validated components from Phase 3. This is the 'basic prototype approach' AgriCom has asked for. The index is not a forecast model at this stage — it is a structured signal that combines the drivers identified in H1–H5 into a single interpretable series. The ARIMAX forecasting architecture remains documented as a future phase, but is not built now.

SCOPE NOTE The two-stage ARIMAX model from the previous roadmap is appropriate as a next phase once the prototype index is validated. It should be described in the final report as the 'full model path' — showing AgriCom that the team has thought beyond the prototype — but it should not be presented as current work. Building it now would produce a sophisticated output with unvalidated inputs, which is the opposite of what AgriCom has asked for.

## 6.1  Construct the product-level index D(p,w)

| Next step: do this - Normalise each component to 0–1 scale: GT_norm = GT/100; ΔP_norm = 1 − (P_organic/P_conventional), clipped to [0,1]; Weather_norm = 0.6·Temp_norm + 0.4·Sunshine_norm. - Construct D(p,w) under three weight specifications: baseline (0.40/0.35/0.25), search-dominant (0.60/0.25/0.15), price-dominant (0.25/0.60/0.15). These directly correspond to the H2 sensitivity analysis. - Plot D(p,w) for each product under the baseline specification. Annotate with key events. Check: does the index respond sensibly to documented episodes? (Expected: spike during 2022/2023 Berlin heatwaves for cucumber and pepper; dip during cost-of-living pressure period for pepper as premium product). - Disclose the GT circularity explicitly in the methodology: GT enters both the index construction and the H1 test. The index cannot be used to validate its own GT component. |  | Final report: include this - Plot the product-level D(p,w) time series as a key figure. Annotate it. This is the prototype — the reader should be able to look at it and say 'yes, that pattern makes sense given what I know about the Berlin organic market.' - Include the three-specification sensitivity plot for one product (tomatoes recommended, as highest basket weight). Show that the index shape is broadly robust to weight choice, while noting where the specifications diverge. - State the construction methodology in one clear paragraph, with the normalisation formula written out explicitly. Transparency here is not optional — it is what makes the output credible. |
| --- | --- | --- |

## 6.2  Construct the basket composite index

| Next step: do this - Combine the four product indices: BasketIndex(w) = 0.35·D(tomato,w) + 0.30·D(greens,w) + 0.20·D(cucumber,w) + 0.15·D(pepper,w). - Plot the basket index over the full panel. Compute its correlation with each product's individual index — this shows which product drives the basket signal most strongly. - Run a simple retrospective check: identify the three highest and three lowest basket index weeks in the panel. Do they correspond to identifiable market events? If yes, this is your strongest single piece of prototype validation. |  | Final report: include this - Include the basket index time series as the final integrating figure of Part 3. It should visually summarise the full analytical narrative: seasonal structure, weather sensitivity, price effects. - Include the retrospective check as a narrative box: 'The three highest-demand weeks in the index correspond to [events]. The three lowest correspond to [events]. These patterns are consistent with known Berlin organic market dynamics.' - Close the empirical section with a clear statement of what the prototype shows and what it does not: 'The basket index produces a plausible, event-consistent signal of relative organic produce demand in Berlin. Full quantitative validation requires proprietary volume data, which is outside the scope of this study. The index is suitable for directional analysis and framework demonstration at this stage.' |
| --- | --- | --- |

# 7.  Scope Boundary — What Not to Build Now

Given AgriCom's expectation of a simple, credible first output, the following components from the previous roadmap are explicitly deferred. They are not abandoned — they represent the logical next phase — but building them now would consume time and produce outputs whose sophistication exceeds their current evidential basis.

| Component | Status | Rationale | When to build |
| --- | --- | --- | --- |
| ARIMAX forecasting model | Deferred | Requires a validated index as input. Forecasting accuracy on an unvalidated proxy is not meaningful to report. | Phase 2 of the project, once prototype index is validated against at least one independent benchmark |
| Four-season H4 spatial weighting | Partially deferred | Run four-season H4 regressions as planned — they are simple and informative. Do not build the full spatial weight surface for ARIMAX distribution yet. | When ARIMAX is built |
| Dominance / relative importance decomposition | Deferred | Useful once the model is estimated. Running it on a proxy index with construction-weight circularity produces misleading importance rankings. | After ARIMAX estimation |
| Rolling 4-week ahead forecast | Deferred | Requires ARIMAX. Not a Phase 1 deliverable. | Phase 2 of the project |
| Directional hit rate evaluation | Deferred | Requires a forecast to evaluate. | After ARIMAX estimation |

The final report should include a clearly labelled 'Future Development' section that briefly describes the ARIMAX architecture and what it would add. This demonstrates methodological ambition to AgriCom without overclaiming the current output. Two paragraphs and the architecture diagram from the previous roadmap is sufficient.

# 8.  Final Report Checklist

The following checklist maps every required component of the final report to its source. Use this to track completion and ensure nothing is missing at submission.

| Report component | Source | Ready? |
| --- | --- | --- |
| Executive summary (1 page) | Written last, summarising Parts 1–3 | No |
| Part 1: Basket composition and weighting rationale | March 13 update — condense to ~1.5 pages | Yes (needs editing) |
| Part 1: Consumer segment typology (5 segments) | March 13 update, Section 3 — condense to ~1 page | Yes (needs editing) |
| Part 1: Driver hierarchy (search, price, weather, seasonality) | Revised data strategy + this outline | Yes (needs editing) |
| Part 1: Index construction formula and normalisation | Phase 4 of this outline | No — build in Phase 4 |
| Part 1: Honest validity statement | Validated discussion from prior session | Yes (needs editing) |
| Part 2: H1–H5 testing plan with revised methods | Hypothesis validation addendum — condense to ~2 pages | Yes (needs editing) |
| Part 3: Data summary table | Phase 1 output | No — build in Phase 1 |
| Part 3: Annotated GT time-series chart (4 products) | Phase 2 exploratory output | No — build in Phase 2 |
| Part 3: Correlation matrix / heatmap | Phase 2 exploratory output | No — build in Phase 2 |
| Part 3: H1a ACF plot + H1b Spearman rank table | Phase 3 H1 output | No — build in Phase 3 |
| Part 3: H2 MAD comparison table (3 index variants) | Phase 3 H2 output | No — build in Phase 3 |
| Part 3: H3 elasticity table (4 products) | Phase 3 H3 output | No — build in Phase 3 |
| Part 3: H4 coefficient table + Berlin choropleth map | Phase 3 H4 output | No — build in Phase 3 |
| Part 3: H5 scatter plot + distributed lag coefficient table | Phase 3 H5 output | No — build in Phase 3 |
| Part 3: Basket index time series (annotated) | Phase 4 output | No — build in Phase 4 |
| Part 3: Retrospective validation narrative | Phase 4 output | No — build in Phase 4 |
| Future development section (ARIMAX path, 2 paragraphs) | Previous roadmap architecture section | Yes (needs editing) |
| References | All prior documents | Yes (compile) |

# 9.  Indicative Timeline

| Phase | Key outputs | Gate |
| --- | --- | --- |
| Phase 1 — Data assembly | GT panel complete; Open-Meteo panel complete; price panel started (AMI or AgriCom) | All public data collected before Phase 2 begins |
| Phase 1 complete + Phase 2 begins | Master panel aligned and audited; exploratory plots and correlation matrix produced | Master panel complete and version-controlled |
| Phase 2 complete + Phase 3 begins | Seasonal decomposition done; H5 run (first result); H1 run | H5 and H1 results reviewed before H2/H3 proceed |
| Phase 3 — H2, H3, H4 | All five hypotheses tested; results tables produced; H4 choropleth drafted | H1–H5 results internally reviewed |
| Phase 4 begins | Product-level index D(p,w) constructed and plotted; basket index constructed | Index passes retrospective event check |
| Phase 4 complete + report writing begins | Prototype index complete; all figures production-ready; report outline filled in | All analytical outputs locked |
| Report writing and review | Full report draft; internal review; revisions | Final report ready for submission |

References and Prior Documents

AgriCom / ESMT Berlin. (2026, March 13). Project Progress Update. [Internal document]

AgriCom / ESMT Berlin. (2026, March). Revised Data Strategy — Addendum A. [Internal document]

AgriCom / ESMT Berlin. (2026, March). Hypothesis Testing Validation — Addendum B. [Internal document]

Agrarmarkt Informations-Gesellschaft (AMI). Markt-Bilanz Gemüse. Annual editions. https://www.ami-informiert.de

Bund Ökologische Lebensmittelwirtschaft (BÖLW). (2025). Die Bio-Branche 2025. https://www.boelw.de

Choi, H., & Varian, H. (2012). Predicting the present with Google Trends. Economic Record, 88, 2–9.

Fleder, D., & Shah, D. (2019). Scalable estimation of geographic search interest. Working paper.

Goel, S., Hofman, J. M., Lahaie, S., Pennock, D. M., & Watts, D. J. (2010). Predicting consumer behavior with web search. PNAS, 107(41), 17486–17490.

Hughner, R. S. et al. (2007). Who are organic food consumers? Journal of Consumer Behaviour, 6(2–3), 94–110.

Murray, K. et al. (2010). The effect of weather on consumer spending. Journal of Retailing and Consumer Services, 17, 512–520.

Boone, T. et al. (2018). Can Google Trends improve your sales forecast? Production and Operations Management, 27(10), 1770–1774.